## 1. Product Overview
Item | Description
Product Name | FarmTrace – AgriFood Supply Chain Intelligence Platform
Product Vision / Purpose | To build the world's most connected agricultural data infrastructure — unifying farm-level data across livestock, feed, genetics, and logistics — enabling full traceability from farm to fork for retailers, processors, and regulators.
Business Goals / Key Success Factors | 1. Onboard 500+ farms across EU & US by Q2 2026 2. Achieve end-to-end traceability for cattle supply chain within v1.0 3. Reduce data reconciliation time for supply chain partners by 60% 4. Attain regulatory compliance with EU Farm-to-Fork & EUDR standards 5. Reach 100,000 platform users by end of 2026
Primary Stakeholders | • Product Manager – Melanie Murk (VP, FarmTrace) • Backend Dev Team – API & Data Integration • Frontend Dev Team – Dashboard & Mobile App • QA / Test Lead – Test Automation • Farm Partners – Livestock farmers (EU & US) • Enterprise Clients – Retailers, Meat Processors, Feed Suppliers • Investors – Surmount Ventures, CNBB Equity Partners

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E1 | Farm Onboarding | US1 | As a farm manager, I want to register my farm profile so that my data is linked to the supply chain. | Farm registration form, GIS map pin, farm ID generation | Must Have | 8 | To Do | Backend Team | Farm registration flow test | QA Lead
|  | US2 | As an admin, I want to verify and approve farm profiles so that only valid farms are onboarded. | Admin dashboard, email notification, approval workflow | Must Have | 5 | To Do | Backend Team | Approval workflow test | QA Lead
|  | US3 | As a farmer, I want to connect my existing farm management system via API so that my data syncs automatically. | Farm Data API integration, OAuth2, webhook support | Must Have | 13 | In Progress | Integration Team | API sync test cases | QA Lead
E2 | Animal Traceability | US4 | As a livestock farmer, I want to log each animal's birth, health, and movement so that I have a full audit trail. | Animal ID (RFID/EID), event logging, timeline view | Must Have | 13 | In Progress | Backend Team | Animal lifecycle test | QA Lead
|  | US5 | As a retailer, I want to scan a QR code on a product and see the animal's full farm history. | QR code generation, consumer-facing trace page, batch linking | Must Have | 8 | To Do | Full-Stack Team | QR scan traceability test | QA Lead
|  | US6 | As a processor, I want to record slaughter and processing events linked to animal IDs. | Processing event API, batch splitting, chain-of-custody record | Should Have | 8 | To Do | Backend Team | Processing event test | QA Lead
E3 | Supply Chain Dashboard | US7 | As a supply chain manager, I want a real-time dashboard showing farm-to-fork status of all batches. | Dashboard widgets, live data feed, filter by farm/batch/date | Should Have | 13 | In Progress | Frontend Team | Dashboard data accuracy test | QA Lead
|  | US8 | As an analyst, I want to export supply chain reports in CSV/PDF so I can share with stakeholders. | Export engine, PDF template, scheduled email reports | Should Have | 5 | To Do | Frontend Team | Export format test | QA Lead
E4 | Compliance & Certification | US9 | As a compliance officer, I want to generate EUDR-compliant traceability reports automatically. | EUDR report template, deforestation data API, digital signature | Must Have | 13 | To Do | Backend Team | EUDR report generation test | QA Lead
|  | US10 | As a farm, I want to track my antibiotic and hormone usage logs so I meet regulatory standards. | Input log form, threshold alerts, audit export | Must Have | 8 | To Do | Backend Team | Threshold alert test | QA Lead
E5 | Notifications & Alerts | US11 | As a supply chain partner, I want to receive alerts when a batch is delayed or flagged. | Alert engine, push/email notification, severity levels | Should Have | 5 | To Do | Backend Team | Alert delivery test | QA Lead
|  | US12 | As a farmer, I want to receive reminders for health checks and certifications due dates. | Calendar-based trigger, in-app + SMS notification | Could Have | 3 | To Do | Backend Team | Reminder trigger test | QA Lead
E6 | Mobile App | US13 | As a field agent, I want a mobile app to log farm data offline so I can sync when connected. | React Native app, offline SQLite storage, background sync | Should Have | 20 | To Do | Mobile Team | Offline sync test | QA Lead
|  | US14 | As a farmer, I want to view my farm's performance stats on my phone. | Mobile dashboard, chart components, responsive UI | Could Have | 8 | To Do | Mobile Team | Mobile UI test | QA Lead
E7 | Feed & Genetics Integration | US15 | As a feed supplier, I want to connect my product catalogue so farms can log feed consumption linked to supply. | Feed supplier API, product catalogue sync, consumption log | Could Have | 8 | To Do | Integration Team | Feed data sync test | QA Lead
|  | US16 | As a genetics company, I want to link animal DNA/breed data to farm profiles for quality tracking. | Genetics data schema, breed tagging, lineage report | Won't Have | 13 | To Do | Backend Team | Genetics link test | QA Lead
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release | Target Date | Key Features | Dependencies | Demo Status
v0.1 | 2026-01-15 | Farm Onboarding (E1): Farm registration, profile verification, API connection | None | ✅ Done
v0.2 | 2026-02-01 | Animal Traceability (E2): Animal ID logging, event tracking, QR code generation | Farm Data API ready | ✅ Done
v0.3 | 2026-02-22 | Supply Chain Dashboard (E3): Real-time dashboard, batch status, filters | Backend API v2 | 🔄 In Progress
v0.4 | 2026-03-08 | Compliance (E4): EUDR reports, antibiotic/hormone logs, digital audit trail | Regulatory templates | 📋 Planned
v0.5 | 2026-03-22 | Notifications (E5): Batch alerts, health check reminders, SMS/email | Notification service | 📋 Planned
v1.0 | 2026-04-12 | Mobile App (E6): Offline logging, mobile dashboard, background sync | React Native setup | 🗓 Yet to Plan
v1.1 | 2026-05-01 | Feed & Genetics (E7): Feed supplier API, genetics breed tagging, lineage reports | Partner API agreements | 🗓 Yet to Plan
v1.1 | 2025-12-27 |  |  | Yet to Plan

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Agile ceremonies (standups, sprint planning) ran smoothly across all teams | Animal data sync had latency issues during high-load testing | Optimize API batch size and add caching layer in next sprint | Backend Lead
Farm onboarding UX received positive feedback from pilot farmers | EUDR compliance requirements were underestimated — delayed v0.4 | Bring in compliance consultant earlier in sprint planning | Product Manager
QR code traceability feature delivered ahead of schedule | Mobile offline sync had edge-case bugs on low-memory devices | Add device compatibility tests to CI/CD pipeline | QA Lead
Team collaboration between frontend and backend improved with shared API contracts | Test coverage for edge cases (e.g., batch splits) was insufficient | Mandate minimum 80% test coverage before PR merges | QA Lead
Integration with VSM farm management system was seamless | Retrospective action items from previous sprint were not tracked | Add action item tracker to Jira and review at start of each sprint | Scrum Master